## Sheet1
Intructions: In the task section, add tasks that your project will need tohave completed. The role column should be either individual team members or entire teams responsible for executing the task. Responsible: The person or group who performs the task. Accountable: The person who is ultimately answerable for the task and its outcome. Consulted: The person or group who needs to be consulted before a decision or action is taken. Informed: The person or group who needs to be kept informed about the progress or outcome of the task.
Task | Role | Responsible | Accountable | Consulted | Informed
1. Requirements Gathering
Define project scope | Business Analyst | ✓ | Project Manager | Development Team, QA Team | Stakeholders
Gather and document user requirements | Business Analyst | ✓ | Project Manager | Development Team, QA Team | Stakeholders
Create use case scenarios | Business Analyst | ✓ | Project Manager | Development Team, QA Team | Stakeholders
2. Design
Develop system architecture | System Architect | ✓ | Technical Lead | Development Team | Project Manager, QA Team
Design database schema | Database Administrator | ✓ | Technical Lead | Development Team | Project Manager
Design user interface (UI) and user experience (UX) | UI/UX Designer | ✓ | Project Manager | Development Team, QA Team | Stakeholders
3. Development
Write code | Development Team | ✓ | Technical Lead |  | Project Manager, QA Team
Conduct code reviews | Development Team | ✓ | Technical Lead |  | Project Manager
Unit testing | Development Team | ✓ | Technical Lead |  | Project Manager, QA Team
4. Testing
Create test plan | QA Team | ✓ | QA Lead | Development Team | Project Manager
Execute test cases | QA Team | ✓ | QA Lead | Development Team | Project Manager
Report and track bugs | QA Team | ✓ | QA Lead | Development Team | Project Manager
5. Deployment
Prepare deployment environment | System Administrator | ✓ | Technical Lead | Development Team | Project Manager, QA Team
Deploy code to production | System Administrator | ✓ | Technical Lead | Development Team | Project Manager, QA Team
Post-deployment monitoring | System Administrator | ✓ | Technical Lead | Development Team | Project Manager, QA Team
6. Project Management
Manage project schedule and budget | Project Manager | ✓ |  | Development Team, QA Team, Stakeholders
Risk management | Project Manager | ✓ |  | Development Team, QA Team, Stakeholders
Communication and reporting | Project Manager | ✓ |  | Development Team, QA Team, Stakeholders